## AUTH UAT Report
Project | DOVA Agricultural Marketplace
Module | Authentication (AUTH-01 to AUTH-09)
Environment | Staging (https://dova.dntech.id)
Tester | Keresia Karuma
Execution Date | 07 August 2026
Summary
Metric | Result
Total Test Cases Executed | 9
Passed | 9
Failed | 0
Blocked | 0
Pass Rate | 100%
Detailed Results
Test ID | Scenario | Expected Result | Actual Result | Status
AUTH-01 | Customer Registration | Customer registers successfully | Registration completed and redirected to customer dashboard. | PASS
AUTH-02 | Registration Validation | Validation messages displayed | Validation messages displayed for invalid inputs. | PASS
AUTH-03 | Duplicate Email | Duplicate email rejected | System prevented duplicate registration. | PASS
AUTH-04 | Customer Login | Successful login | Logged in successfully with valid credentials. | PASS
AUTH-05 | Invalid Login | Reject invalid credentials | Invalid credentials rejected with error message. | PASS
AUTH-06 | Logout | Cookies/session cleared; protected routes blocked | Logged out successfully, redirected to login; protected pages required authentication. Browser autofill confirmed as browser behaviour. | PASS
AUTH-07 | Customer Role Guard | Customer blocked from /admin | Redirected to Home page; Admin inaccessible. | PASS
AUTH-08 | Supplier Role Guard | Pending supplier blocked | Application under review displayed; supplier dashboard inaccessible until approval. | PASS
AUTH-09 | Guest Checkout Authentication | Guest prompted to login | Login modal displayed before adding to cart; customer could continue after login. | PASS
Conclusion
Authentication module successfully passed all executed UAT scenarios (AUTH-01 to AUTH-09). Overall Result: PASS.

## Catalog and Search
Test Case ID | Module | Scenario | Test Steps | Expected Result | Actual Result | Status | Evidence / Screenshot | Bug ID | Comments
CAT-01 | Catalog & Search | Browse products | 1. Open Products/Catalog page 2. Allow page to load 3. Confirm product grid/list loads 4. Check product prices 5. If more than 12 products, check pagination | Product grid loads; prices are displayed; pagination is available if there are more than 12 products. | Products catalog loaded successfully. Product cards displayed product names, prices and available stock. Pagination was available and Page 2 loaded successfully. | PASS |  | N/A
CAT-02 | Catalog & Search | Search | 1. Open Products/Catalog 2. Enter a product name in search 3. Verify results | Correct product is returned when searching by product name. | Entered “Chicken” in the product search field. The catalog successfully filtered the results and displayed the relevant “Chicken Breast” product. | PASS |  | N/A
CAT-03 | Catalog & Search | Category filter | 1. Open Products/Catalog 2. Select a category 3. Review displayed products | Product list filters correctly according to the selected category. | Selected the pantry, vegetables, meat, dairy, grains, beverages and seafood from the category. The catalog successfully filtered the product list and displayed products in each category: No products from other categories were displayed. | PASS |  | N/A
CAT-04 | Catalog & Search | Product detail | 1. Open Products/Catalog 2. Select a product 3. Review the product detail page | Product details show name, price, stock, supplier and description. | Selected Organic Bananas from the catalog. The product detail page opened successfully and displayed the product name, price, available stock, supplier and product description as expected. | PASS |  | N/A
CAT-05 | Catalog & Search | Verified badge | 1. Locate a product from an approved supplier 2. Open/view the product 3. Check for verification indicator | Products from approved suppliers display a Verified indicator where applicable. | Opened Premium rice supplied by Green Valley Farms. The product detail page displayed a “Verified” badge next to the approved supplier information. | PASS |  | N/A
CAT-06 | Catalog & Search | Mobile layout | 1. Open /products on a phone/mobile width 2. Check navigation 3. Review product cards 4. Scroll and interact with the page | Mobile layout has usable navigation and readable product cards. | Product page was tested on a mobile device. The layout adapted correctly to the mobile screen, navigation remained accessible through the hamburger menu, and product information and controls were clearly readable and usable. | PASS |  | N/A

## Cart and delivery slot
Test Case ID | Module | Scenario | Test Steps | Expected Result | Actual Result | Status | Evidence / Screenshot | Bug ID | Comments
CART-01 | Cart & Delivery Slot | Add to cart | 1. Open a product 2. Select delivery slot 3. Click Add to Cart 4. Open cart and verify item | Item is added to cart with the selected delivery slot. | Crisp Carrots was successfully added to the shopping cart with a quantity of 5 kg. The selected Morning delivery slot was retained and displayed in the cart. The cart correctly calculated the total as ₦80,000. | PASS |  | N/A
CART-02 | Cart & Delivery Slot | Slot required | 1. Open a product 2. Do not select morning/evening 3. Click Add to Cart | System prevents adding and displays an error such as “select delivery slot”. | No error message is displayed when the user attempts to add a product without selecting a delivery slot. | FAIL | attached separately | BUG-004
CART-03 | Cart & Delivery Slot | Update quantity | 1. Open /cart 2. Increase quantity 3. Decrease quantity 4. Check total after each change | Quantity updates correctly and the total recalculates accurately. | Updated product quantities in the shopping cart. The system successfully recalculated the line totals according to the selected quantities. Crisp Carrots at ₦16,000 × 10 kg displayed ₦160,000, and Farm Milk at ₦22,000 × 5 kg displayed ₦110,000. | PASS |  | N/A
CART-04 | Cart & Delivery Slot | Change slot | 1. Open /cart 2. Change delivery slot on a line item 3. Refresh/reopen cart if appropriate | The newly selected morning/evening delivery slot is persisted. | Changed the delivery slot for the cart item from Morning to Evening. After refreshing the cart page, the newly selected Evening delivery slot remained selected, confirming that the change was successfully persisted. | PASS |  | N/A
CART-05 | Cart & Delivery Slot | Stock limit | 1. Identify available stock 2. Set quantity above available stock 3. Attempt to continue | System prevents quantity exceeding available stock and shows an appropriate error. | Available stock was 20 kg. A quantity of 22 kg was entered and the product was added to the cart. The system automatically reduced the quantity to 20 kg, but no warning or validation message was displayed to inform the customer that the requested quantity exceeded available stock. | FAIL | attached separately | BUG-005
CART-06 | Cart & Delivery Slot | Empty cart | 1. Open /cart 2. Remove all items 3. Attempt to proceed to checkout | Cart becomes empty and checkout is blocked. | All items were removed from the shopping cart. The cart displayed an empty-cart message and the Proceed to Checkout option was no longer available, successfully preventing checkout with an empty cart. | PASS |  | N/A
Overall Test Summary
Module: Cart & Delivery Slot
Total Test Cases: 6
Passed: 4
Failed: 2
Pass Rate: 66.7%
Overall Result: FAIL – Defects Found
Tester Summary / Comments:
Cart and Delivery Slot functionality was tested against CART-01 to CART-06. Core cart functionality, quantity recalculation, delivery-slot persistence and empty-cart handling worked as expected. Two defects were identified: the system does not display a validation message when a delivery slot is not selected, and quantities exceeding available stock are automatically reduced without notifying the customer. Both issues should be corrected and retested.

## Bug report
Bug ID | Module | Test Case ID | Bug Title | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Evidence | Environment | Comments
BUG-CART-004 | Cart & Delivery Slot | CART-02 | No validation message displayed when adding product without delivery slot | User attempts to add a product without selecting the required delivery slot. The product is not added, but no validation feedback is displayed. | 1. Log in. 2. Open an in-stock product. 3. Enter/select a valid quantity. 4. Do not select Morning or Evening. 5. Click Add to Cart. | Product should not be added and a clear validation message should prompt the user to select a delivery slot. | Product is not added. No validation/error message appears and the Add to Cart button appears to perform no action. | Medium | Medium | Open | Screenshot/video to be attached | Dova Chain web application | Found during CART-02 UAT execution.
BUG-CART-005 | Cart & Delivery Slot | CART-05 | Quantity above available stock is silently reduced without notifying customer | When a customer enters a quantity greater than the available stock, the system automatically reduces it to the maximum available stock without notifying the customer. | 1. Open the Fresh Tomatoes product detail page. 2. Confirm available stock is 20 kg. 3. Enter 22 kg. 4. Select a delivery slot. 5. Click Add to Cart. 6. Open the cart and check the quantity. | The system should prevent ordering above available stock and display a clear validation message informing the customer that only 20 kg is available. | The customer entered 22 kg and the system indicated that the product was added to the cart. The quantity was automatically reduced to 20 kg without any warning or validation message. | Medium | Medium | OPEN |  | Dova Chain web application | Found during CART-05 UAT execution.

## Checkout and minimum order
Test Case ID | Module | Scenario | Test Steps | Expected Result | Actual Result | Status | Evidence / Screenshot | Bug ID | Comments
CHK-01 | Checkout & Minimum Order | Delivery below minimum | 1. Add delivery items totaling 4,999 2. Proceed to checkout | Checkout is blocked and the system tells the user how much more must be added to reach the 5,000 minimum. |  | Not Tested
CHK-02 | Checkout & Minimum Order | Delivery at minimum | 1. Add delivery items totaling 5,000 or more 2. Proceed to checkout | Checkout is allowed. |  | Not Tested
CHK-03 | Checkout & Minimum Order | Pickup below minimum | 1. Select pickup 2. Create basket totaling 2,999 3. Proceed to checkout | Checkout is blocked because the 3,000 pickup minimum has not been reached. |  | Not Tested
CHK-04 | Checkout & Minimum Order | Pickup at minimum | 1. Select pickup 2. Create basket totaling 3,000 or more 3. Proceed to checkout | Checkout is allowed and the default hub address is accepted. |  | Not Tested
CHK-05 | Checkout & Minimum Order | Required fields | 1. Start delivery checkout 2. Leave name, phone or address blank 3. Attempt to continue | Validation error is displayed and checkout cannot continue until required fields are completed. |  | Not Tested
CHK-06 | Checkout & Minimum Order | Guest blocked | 1. Log out 2. Attempt checkout as a guest | User is shown a login modal or redirected to login; guest checkout is blocked. |  | Not Tested

## Payments
Test Case ID | Module | Scenario | Test Steps | Expected Result | Actual Result | Status | Evidence / Screenshot | Bug ID | Comments
PAY-01 | Payments | Mock payment flow | 1. Complete checkout 2. Click Pay 3. Complete mock flow 4. Verify order status | System redirects to /checkout/verify and the order is marked Paid after successful verification. |  | Not Tested
PAY-02 | Payments | Mock idempotency | 1. Initialize payment for an order 2. Initialize payment again for the same order 3. Compare references | The same payment reference is reused for the same order. |  | Not Tested |  | May require API/developer access
PAY-03 | Payments | Paystack test payment | 1. Ensure Paystack test keys are configured 2. Checkout 3. Pay using a Paystack test card 4. Complete verification | Paystack test page completes successfully; verification succeeds and the order is marked Paid. |  | Not Tested
PAY-04 | Payments | Webhook | 1. Send valid Paystack charge.success webhook to /payments/webhook 2. Use valid signature 3. Check order | Order is marked Paid when a valid webhook is received. |  | Not Tested |  | May require API/developer access
PAY-05 | Payments | Order history after payment | 1. Complete a successful payment 2. Open /customer or order history 3. Locate the order | The order is listed in customer order history with Paid status. |  | Not Tested

## Supplier
Test Case ID | Module | Scenario | Test Steps | Expected Result | Actual Result | Status | Evidence / Screenshot | Bug ID | Comments
SUP-01 | Supplier | Register | 1. Open /auth/supplier-register 2. Complete registration 3. Upload required documents 4. Submit | Supplier registration succeeds and status is Pending. |  | Not Tested
SUP-02 | Supplier | Pending dashboard | 1. Log in as supplier before approval 2. Open supplier dashboard | Access is limited and a pending/approval message is displayed. |  | Not Tested
SUP-03 | Supplier | Product CRUD | 1. Add a product 2. Edit the product 3. Delete a product 4. Check catalog when active | Add/edit/delete operations work correctly; active supplier products are reflected in the catalog. |  | Not Tested
SUP-04 | Supplier | Image upload | 1. Upload JPG/PNG/WEBP product image ≤5 MB 2. Save product 3. View product image | Supported image is stored and displayed correctly. |  | Not Tested
SUP-05 | Supplier | Stock adjustment | 1. Restock a product or record damaged stock 2. Save adjustment 3. Check stock history | Stock quantity and stock history are updated correctly. |  | Not Tested
SUP-06 | Supplier | Fulfilment status | 1. Move order through pending/paid → processing → shipped → delivered 2. Attempt invalid transition if possible | Only valid fulfilment status transitions are accepted. |  | Not Tested
SUP-07 | Supplier | Stock on purchase | 1. Record supplier stock 2. Customer purchases product 3. Check supplier stock after order | Supplier stock decreases according to the quantity purchased. |  | Not Tested

## Admin
Test Case ID | Module | Scenario | Test Steps | Expected Result | Actual Result | Status | Evidence / Screenshot | Bug ID | Comments
ADM-01 | Admin | Dashboard stats | Log in as Admin; open /admin; review dashboard counts | Dashboard displays users, suppliers, products and orders counts. |  | Not Tested
ADM-02 | Admin | Approve supplier | Open pending suppliers; select test supplier; approve; verify access | Supplier becomes active and can add products. |  | Not Tested
ADM-03 | Admin | Reject supplier | Open pending suppliers; select test supplier; reject with reason; verify status | Supplier becomes inactive/rejected. |  | Not Tested
ADM-04 | Admin | Users / products / orders | Open Users, Products and Orders admin tables; test applicable active/inactive controls | Records display correctly and applicable active/inactive controls work. |  | Not Tested
ADM-05 | Admin | Contacts inbox | Submit contact form; log in as Admin; open contacts/messages | Submitted contact message is visible to Admin. |  | Not Tested

## Public pages and feedlog
Test Case ID | Module | Scenario | Test Steps | Expected Result | Actual Result | Status | Evidence / Screenshot | Bug ID | Comments
PUB-01 | Public Pages & FeedLog | Home page | Open /; review hero, featured content and CTA | Home page renders correctly with hero, featured content and CTA. |  | Not Tested
PUB-02 | Public Pages & FeedLog | About / Contact | Open About and Contact; submit contact form | Pages render and contact submission persists. |  | Not Tested
PUB-03 | Public Pages & FeedLog | Footer links | Click each footer link and verify destination | All footer links open the correct routes. |  | Not Tested
PUB-04 | Public Pages & FeedLog | Feedback - guest | Log out; click Feedback; observe destination | Guest Feedback opens /feedback in the same tab. |  | Not Tested
PUB-05 | Public Pages & FeedLog | Feedback SSO | Log in; click Feedback; verify SSO | When configured, FeedLog SSO signs the user in correctly. |  | Not Tested |  |  | May require environment, API, terminal or developer access.
PUB-06 | Public Pages & FeedLog | External FeedLog disabled | Use environment with integration disabled; inspect feedback links | Feedback links are hidden when integration is disabled. |  | Not Tested |  |  | May require environment, API, terminal or developer access.
PUB-07 | Public Pages & FeedLog | Dashboard Feedback | Check Feedback as Admin, Supplier and Customer | Feedback entry points for logged-in roles lead to /feedback. |  | Not Tested

## staging Go live (ops)
Test Case ID | Module | Scenario | Test Steps | Expected Result | Actual Result | Status | Evidence / Screenshot | Bug ID | Comments
OPS-01 | Staging Go-Live | Health endpoint | Send GET /api/v1/health against staging; inspect response | API responds with {"status":"ok"}. |  | Not Tested |  |  | May require environment, API, terminal or developer access.
OPS-02 | Staging Go-Live | Staging smoke tests | Run npm run smoke:week4 against staging API; review results | Smoke test suite passes. |  | Not Tested |  |  | May require environment, API, terminal or developer access.
OPS-03 | Staging Go-Live | Paystack test transactions | Perform at least 10 Paystack test transactions; verify each and webhook | All transactions verify successfully and webhook processing works. |  | Not Tested |  |  | May require environment, API, terminal or developer access.
OPS-04 | Staging Go-Live | Mobile smoke journey | On real phone complete customer, supplier and admin journeys | Full journeys work successfully on mobile. |  | Not Tested